# Appendix 3. Checklist to support the planning of a PHEPA– country checklist

| Appendix name | Function | When to use it | Purpose |
| --- | --- | --- | --- |
| 3. Planning checklist | Checklist to support the country during the planning phase of the assessment process | Preparatory period, before and during the country visit and afterwards | For information. |

## Phase 1 – Desk review

| Check mark | When to perform task | Task description |
| --- | --- | --- |
|  | Around six months before the country visit | The country has received and replied to the official invitation letter |
|  | Around five months before the country visit | The country has nominated a Focal Point (a person or a team) - Please, note that the Focal Point will have to coordinate and ensure engagement from several sectors and levels in the country. Further details are available in the Appendix 1 ToR. Section 2 |
|  | Around five months before the country visit | The country has confirmed the dates for the country visit |
|  | Around five months before the country visit | The country has identified and shared with ECDC the fifth capacity suggested to be assessed in depth during this cycle |
|  | Around five months before the country visit | The country has informed about any potential need of interpretation services during the country visit |
|  | Around five months before the country visit | The country has nominated the experts that should have access to the SharePoint to support the documentation sharing process |
|  | Around five months before the country visit | The country has been informed and expressed its opinion about the presence of experts from WHO Euro and from another EU/EEA country joining the assessment |
| No action | Around five months before the country visit | The country has received the PHEPA Practical guide with relevant Appendices - This is the document describing all the steps and relevant information to consider planning for the PHEPA The country has received the Assessment tool - This is the document that the assessment team will use as the basis to guide the assessment group discussions during the country visit |
|  | Before the country visit | The country has booked the rooms for the in-country visit sessions - Consider round table/board room settings for the sessions to facilitate an inclusive discussion - Consider avoiding theatre setting rooms - Check with the ECDC coordination team during the logistical preparatory meetings the number of rooms needed and any other logistical requirement |
|  | Around three to four months before the country visit | The country has revised and confirmed the agenda - The times and order of the sessions are still indicative, consider adapting the agenda according to the national experts’ and country’s convenience at a later stage |
|  | Around two to three months before the country visit | The country has identified the Capacity Leads and the national experts that will participate in the PHEPA - Suggestions about relevant national stakeholders is available in Appendix 2. Please, consider ensuring regional participation in the assessment if relevant. Please complete with this information the Appendix 1. ToR. Section 1. Table iii. National experts participating to the assessment process |
|  | Minimum six weeks before the country visit | The country has shared the relevant documents for each capacity with the assessment team - Share only the documents that are considered relevant to support the assessment of the aspects included in the PHEPA. Further information on the documents is available in Appendix 4. |
|  | Anytime | To communicate with ECDC assessment team if any clarification is needed |

## Phase 2 – Country visit

| Check mark | When to do it | Task description |
| --- | --- | --- |
|  | Prior and during the country visit | The country has ensured the presence of all relevant stakeholders during the appropriate time |
|  | Prior and during the country visit | The country has ensured the presence of the country Focal Point to coordinate with national experts and the assessment team over the full week |
|  | Prior and during the country visit | The country has set the venue, logistical needs, and other necessary arrangements for the country visit |
|  | Prior and during the country visit | The Capacity Leads are informed about the presentations expected for all the sessions - An overview of each capacity with a focus on the information reported under Article 7 and SPAR is expected for all the capacities - For the capacities not assessed in-depth a maximum of 10 minutes is proposed, for the in-depth capacities a maximum 20 minutes presentation is expected. Further information can be found in the practical guide under section 7.3 and a suggested template is available as Appendix 8. |

## Phase 3 – ECDC assessment report and Phase 4 – Country action plan

| Check mark | When to do it | Task description |
| --- | --- | --- |
| No action | Two weeks after the end of the country visit | The country has received the draft assessment report developed by the assessment team |
|  | Within three to four weeks after receiving the draft report | The country has reviewed the assessment report and returned it including feedback - It is suggested to share the report with all the relevant stakeholders that participated in the assessment process - This will be the only round of feedback. Exceptional needs will be considered. |
|  | Within three weeks from sending the comments to ECDC | The country has received the final assessment report |
|  | Within nine months of receiving the final assessment report | The country has developed or updated an existing action plan incorporating the recommendations included in the assessment report and has presented the Action Plan to the Commission and to ECDC - Please, note that if the country decides not to follow a recommendation included in the assessment report, they should present the reasons for so deciding following Appendix 10 |